## Sheet1
WBS | Activity | Predecessors | Duration | ES | EF | LS | LF | Total Float
TRN000 | GCCG e-Banking Portal
TRN001 | Systems Engineering
TRN001.1 | Technical Planning
TRN001.1.1 | Create technical plan |  | 10 Days | 0 | 10 | 0 | 10 | 0
TRN001.1.2 | Estimate resources | TRN001.1.1 FS | 4 Days | 10 | 14 | 10 | 14 | 0
TRN001.1.3 | Plan reviews | TRN001.1.2 FS | 5 Days | 14 | 19 | 14 | 19 | 0
TRN001.1.4 | Plan authorization | TRN001.1.3 FS | 2 Days | 19 | 21 | 19 | 21 | 0
TRN001.2 | Technical Supervision
TRN001.2.1 | Analyze technical requirements | TRN001.1 FS + 5 Days | 5 Days | 26 | 31 | 26 | 31 | 0
TRN001.2.2 | Document supervision plan | TRN001.2.1 FS | 2 Days | 31 | 33 | 31 | 33 | 0
TRN001.2.3 | Review supervision plan | TRN001.2.2 FS | 1 Day | 33 | 34 | 33 | 34 | 0
TRN001.2.4 | Obtain authorization | TRN001.2.3 FS | 1 Day | 34 | 35 | 14 | 35 | 0
TRN001.3 | Business Requirements Definition
TRN001.3.1 | Gather requirements | TRN001.2 FS | 4 Days | 35 | 39 | 51 | 55 | 16
TRN001.3.2 | Document business requirements | TRN001.3.1 FS | 2 Days | 39 | 41 | 55 | 57 | 16
TRN001.3.3 | Review requirements | TRN001.3.2 FS | 1 Day | 41 | 42 | 57 | 58 | 16
TRN001.3.4 | Obtain authorization | TRN001.3.3 FS | 1 Day | 42 | 43 | 58 | 59 | 16
TRN001.4 | Systems Requirements Definition
TRN001.4.1 | Conduct meetings | TRN001.3 SS | 10 Days | 35 | 45 | 35 | 45 | 0
TRN001.4.2 | Document requirements | TRN001.4.1 FS | 10 Days | 45 | 55 | 45 | 55 | 0
TRN001.4.3 | Review requirements | TRN001.4.2 FS | 3 Days | 55 | 58 | 55 | 58 | 0
TRN001.4.4 | Obtain authorization | TRN001.4.3 FS | 1 Day | 58 | 59 | 58 | 59 | 0
TRN001.5 | System Architecture & Top-Level Design
TRN001.5.1 | Select project system architecture | TRN001.4 FS, TRN001.3 FS | 5 Days | 59 | 64 | 59 | 64 | 0
TRN001.5.2 | Develop system architecture | TRN001.5.1 FS | 10 Days | 64 | 74 | 64 | 74 | 0
TRN001.5.3 | Conduct analysis and review | TRN001.5.2 FS | 10 Days | 74 | 84 | 74 | 84 | 0
TRN001.5.4 | Obtain authorization | TRN001.5.3 FS | 1 Day | 84 | 85 | 84 | 85 | 0
TRN001.6 | Systems Engineering COMPLETE |  | 0 Day