## Sheet1
WBS | Activity | Predecessors | Resource Name | Duration
TRN000 | GCCG e-Banking Portal
TRN001 | Systems Engineering
TRN001.1 | Technical Planning
TRN001.1.1 | Create technical plan |  | Technical Experts, Software Development Leads | 10 Days
TRN001.1.2 | Estimate resources | TRN001.1.1 FS | Project Manager, Technical Experts, Functional Managers | 4 Days
TRN001.1.3 | Plan reviews | TRN001.1.2 FS | Project Manager, Technical Experts, Users | 5 Days
TRN001.1.4 | Plan authorization | TRN001.1.3 FS | Users, Project Manager | 2 Days
TRN001.2 | Technical Supervision
TRN001.2.1 | Analyze technical requirements | TRN001.1 FS + 5 Days | Technical Experts, Software Architects, Software Development Leads, Team Members, Users | 5 Days
TRN001.2.2 | Document supervision plan | TRN001.2.1 FS | Technical Experts, Software Development Leads | 2 Days
TRN001.2.3 | Review supervision plan | TRN001.2.2 FS | Technical Experts, Software Architects, Project Manager | 1 Day
TRN001.2.4 | Obtain authorization | TRN001.2.3 FS | Project Manager, PMO | 1 Day
TRN001.3 | Business Requirements Definition
TRN001.3.1 | Gather requirements | TRN001.2 FS | Technical Experts, Software Architects, Project Manager, PMO | 4 Days
TRN001.3.2 | Document business requirements | TRN001.3.1 FS | Technical Experts, Software Architects, Project Manager | 2 Days
TRN001.3.3 | Review requirements | TRN001.3.2 FS | Technical Experts, Software Architects, Project Manager, Consultants | 1 Day
TRN001.3.4 | Obtain authorization | TRN001.3.3 FS | Project Manager, PMO | 1 Day
TRN001.4 | Systems Requirements Definition
TRN001.4.1 | Conduct meetings | TRN001.3 SS | Technical Experts, Software Architects, Software Development Leads, Consultants, Project Team Members, Project Manager | 10 Days
TRN001.4.2 | Document requirements | TRN001.4.1 FS | Technical Experts, Software Architects, Consultants, Project Team Members | 10 Days
TRN001.4.3 | Review requirements | TRN001.4.2 FS | Technical Experts, Software Architects, Project Manager, Consultants | 3 Days
TRN001.4.4 | Obtain authorization | TRN001.4.3 FS | Project Manager, PMO | 1 Day
TRN001.5 | System Architecture & Top-Level Design
TRN001.5.1 | Select project system architecture | TRN001.4, TRN001.3 | Software Architects, Technical Experts, Software Development Leads, Project Manager | 5 Days
TRN001.5.2 | Develop system architecture | TRN001.5.1 FS | Software Architects, Technical Experts, Software Development Leads, Project Team Members | 10 Days
TRN001.5.3 | Conduct analysis and review | TRN001.5.2 FS | Software Architects, Technical Experts, Software Development Leads, Project Manager, Project Team Members | 10 Days
TRN001.5.4 | Obtain authorization | TRN001.5.3 FS | Project Manager, PMO, Senior Manager | 1 Day
TRN001.6 | Systems Engineering COMPLETE |  |  | 0 Days