## Slide 1: Defining Project Management Fundamentals
Identify Project Management Basics
Describe the Project Life Cycle
Identify Organizational Influences on Project Management
Define Agile Methodology

## Slide 2: Projects
A temporary work endeavor.
Creates a unique product, service, or result.
Has a clearly defined beginning and end.
Example: Creating an intranet website that displays employee information.

## Slide 3: Subprojects
An independently manageable component of an existing project.
Can have smaller subprojects.
Can be contracted either to:
  An external enterprise.
  Another functional unit in the organization.
  Example: Creating the interior design for a solar powered car. Subprojects contracted to vendors are:
  The designing of seats.
  The air-conditioning system.

## Slide 4: Project Management
Planned effort for executing and monitoring a project in order to accomplish its defined goals and objectives.
Managing projects involves:
  Scheduling.
  Identifying requirements.
  Establishing objectives.
  Balancing quality, scope, time, and cost.
  Addressing the concerns and expectations of the stakeholders.
  Example: A project manager’s responsibilities include:
  Communicating cross-functionally.
  Managing people who do not report directly to them.
  Delivering the work on time and within the specified budget and quality specifications.

## Slide 5: Programs
A group of related projects that have a common objective.
Offer great control over constituent projects.
Deliver benefits that the organization can use to meet its goals.
  Example: A computer service company expanding its business. Projects include:
    Conducting market research to establish demand.
    Constructing new branch stores.
    Selecting franchise.
    Designing the marketing campaign.
    Consolidating customer base by establishing loyalty programs.

## Slide 6: Portfolios
Portfolio
Project
Project
Program
Project
Subproject
Subproject
Operations
HR
Accounting
Purchasing
*Some projects include subprojects, but not all projects do.
Project
Subproject*

## Slide 7: Operations
Ongoing and repetitive tasks that produce the same outcome every time they are performed.
Purpose of operations includes:
  Carrying out day-to-day organizational functions.
  Generating income to sustain the business.
  Increasing the value of organizational assets.
Aligned with the business requirements of an organization.
  Example: Operations in a computer manufacturing company. Operations include:
  Daily production.
  Routine maintenance.
  Employee wages.
  Grievance handling.
  Logistics.
  Supply of finished products to the market.

## Slide 8: The PMO
A centralized, permanent, ongoing administrative unit of a department that serves to improve project management performance within an organization.
Tries to maintain standards across projects and improve efficiency.
Functions of a PMO include:
  Maintaining project historical information.
  Managing shared resources across projects managed by the PMO.
  Monitoring project timelines, budget, and quality at an enterprise level.
  Identifying and implementing new project management methodologies.
  Creating effective project policies, documentation, and templates.
  Helping project managers develop estimates and schedules.
  Conducting routine quality assurance reviews.
  Managing communication across projects under the PMO.
PMO publishes their policies, templates, and other documentation on an intranet site, or in a wiki library.

## Slide 9: Project Stakeholders
Person who has a business interest in the outcome of a project or who is actively involved in its work.
  Example: An energy company is building a new power plant to harness alternative geothermal energy. Project stakeholders will include:
  Staff, management, and company owners
  Local and statewide elected officials
  Licensing agencies
  Engineers, architects, and construction workers

## Slide 10: Project Stakeholder Types
Customers/end-users
Sponsor/champion
Portfolio managers/Portfolio review board
Program managers
Project Management Office (PMO)
Project managers
Project management team
Project coordinator
Scheduler
Project team
Vendors and business partners
Functional managers
Operations managers

## Slide 11: Positive and Negative Stakeholders
Positive stakeholders usually benefit from the successful outcome of a project. Example: Business leaders definitely benefit from the boost to the local economy after a successful industrial expansion project, and might be prone to assist in accelerating the permit process.
Negative stakeholders see the negative outcomes of a successful project. Example: Environmental groups consider the successful industrial expansion project to be harmful to the environment, and might try to block further progress of the project.

## Slide 12: The Project Manager Role
Responsibilities
  Meet project objectives
  Ensure project plan aligns with program plan
Characteristics
  Knowledge
  Performance
  Personal effectiveness

## Slide 13
Identifying Project Management Basics

## Slide 14: The Project Life Cycle
Projects are broken down into manageable, sequential phases of work.
Consists of project phases (or process groups)
  Initial phase—scope and timing are determined
  Intermediate phases—detailed planning and the actual work happens
  Final phase—closing activities occur
Marked by the beginning and end of the project

## Slide 15: Project Life Cycle Characteristics
A generic project life cycle includes:
  Starting or initiating the project
  Organizing, planning, and preparing
  Carrying out or performing the project work and monitoring the project work
  Closing the project out
Cost and staffing levels change as the project progresses.
  At the start, the levels are relatively low
  As work occurs, the levels increase and reach their peak.
  As the project ends, the levels drop rapidly.

## Slide 16: Project Management Processes
Process is a sequence of activities designed to bring about a specific result.
Project Management Processes are all the activities that provide the effective foundational support for the project management.
Grouped into five process groups:
  Initiating
  Planning
  Executing
  Monitoring and Controlling
  Closing
Produce project deliverables (schedules and performance reports) or product deliverables (new software interface or physical product).

## Slide 17: Project Life Cycle Phases (Process Groups)
Executing
Closing
Planning
Initiating
Monitoring & Controlling

## Slide 18: Tailoring
The process of determining which processes are appropriate for a given project.
Performed by the project manager and the project team.

## Slide 19: Project Life Cycle Outputs
Initiating
Project purpose
Project management plans
Deliverables
Formal acceptance and closure
Change requests
Planning
Goals and objectives
Project Charter
Work Breakdown Structure
Project schedule
Executing
Quality improvements
Proposals and contracts
Monitoring & Controlling
Corrective action
Risk and Issues log
Closing
Project archives
Lessons learned
Transition and training
Scope statement
Project costs

## Slide 20: Project Prototyping
The process of creating a mock-up of a product or an information system.
Usually built for demonstration purposes.

## Slide 21: Prototyping Models
Model | Used to
Proof-of-principle | Check some aspects of the product design without considering the visual appearance, the materials to be used, or the manufacturing process.
Form study | Check the primary size and appearance of a product without simulating its exact function or design.
Visual | Check the design and imitate the appearance, color, and surface textures of the product but will not contain the functions of the final product.
Functional | Check the appearance, materials, and functionality of the expected design.

## Slide 22: Constructing a Stadium
Executing
Closing
Initiating
Monitoring & Controlling
Planning
Stage 2: Stadium Construction
Executing
Closing
Planning
Monitoring & Controlling
Initiating
Stage 1: Site Selection
Executing
Closing
Planning
Monitoring & Controlling
Initiating
Stage 3: Infrastructure Setup

## Slide 23: Project Governance
Methodology carried out throughout the life cycle of a project.
Contains project phase reviews.
Management review is done at the start of every phase.

## Slide 24: Governance Activities in a Project
At the beginning of each phase:
  Verify and validate the former assumptions.
  Analyze risks.
  Explain in detail the processes required to achieve a phase’s deliverables.
A phase-end review is necessary to ensure completeness and acceptance.
A phase-end review signifies the start of the subsequent phase.
A project phase can be closed or a project can be terminated when:
  Huge risks are involved.
  Objectives are not required to be met.

## Slide 25: Phase-Gate Reviews
A check point review of project deliverables and performance at the end of each phase of a project.
Used to check if each phase has fulfilled the exit criteria and is eligible to move to the next step.
Software development projects use a specialized type of phase gate called a quality gate.
Final Project Deliverable
Phase 1
Phase 2
Phase 3
Phase 4
Phase 5
G1
G4
G5
G2
G3
Gn
= Phase-gate reviews

## Slide 26: Phase-to-Phase Relationships in a Project
Multi-phased projects follow sequential process to ensure greater control over the project.
Aids in achieving the desired product, service, or result.
Phase-to-phase relationship types:
  Sequential
  Overlapping
  Iterative
Factors that decide the types of relationships between phases:
  Level of control
  Effectiveness
  Degree of uncertainty

## Slide 27: Phase-to-Phase Relationship Types
Relationship Type | Description
Sequential | Contains consecutive phases. Starts only when previous phase is complete. Reduces the level of uncertainty—produces reliable cost and duration estimates but removes the ability to reduce project duration later in project cycle.
Overlapping | Contains phases that start prior to the completion of preceding phase. Increases the level of risk and can cause rework if phase begins with inaccurate information.
Iterative | Dictates that one phase at a time is planned and carried out. Requires planning for the next phase as the work in the current phase progresses. Is largely helpful in environments that are quite uncertain and undefined. Reduces the need for long-term planning. Minimizes project risk and maximizes the business value of the product. Is an extension, or corollary, of the overlapping relationship—same phase repeats itself multiple times.

## Slide 28: Progressive Elaboration
Add successive layers of detail
Hand-off or deliverable is required
Obtain approval after each phase and before next phase
Can use the rolling wave planning technique that plans near-term work in detail and future work with less detail.

## Slide 29
Describing the Project Life Cycle

## Slide 30: Activity Scenario
Activity | Entity Involved | Comments
Identify locations for setting up branches and infrastructure | Senior management Strategic planning department | 
Recruit banking personnel | CEO Process engineering team Marketing team | Hire and co-locate banking personnel. Compensation for all involved is heavily leveraged toward the variable portion—if the program is successful, all involved will receive bonuses. All aspects of the program are handled through the PMO from this point forward.
Develop banking CRM | PMO Project manager IT staff Software development team | Software will provide access to all functions offered by the bank, such as: Consumer banking e-Banking Mobile banking Credit cards Direct banking
Train banking personnel on banking processes and CRM software | PMO Project manager Training managers | 

## Slide 31: Organizational Cultures and Styles
Factor | Description
Policies | Organizational policies and procedures influence the projects the company undertakes.
Values | Values, beliefs, and expectations of an organization have a major impact on the organizational culture.
Management style | Management style of the organization is another factor that affects the organizational culture.
Work environment | Work ethics followed by the organization also constitute the organizational culture.

## Slide 32: The Organizational Culture's Influence on Projects
Project Aspect | Description
Project policies and procedures | The project policies and procedures should reflect those of the organization.
Project selection | The criteria for the selection of projects are determined by the organizational culture.
Project management style | A project manager should adapt to the management style of an organization.
Team performance assessments | The project manager should adhere to a company's policies when assessing the performance of a team.

## Slide 33: Organizational Process Assets
Entities that influence project success.
Examples include policies, procedures, guidelines, formal and informal plans, templates, lessons learned documents, and historical information.
Project team members handle updates to the assets.
Category | Description
Processes and procedures | Policies, guidelines, templates, and other documented processes that a company uses for performing project-related tasks.
Corporate knowledge base | A repository for storing and retrieving information either on a company intranet site, or in a collaboration software, such as Microsoft Project.

## Slide 34: Enterprise Environmental Factors
Internal and external
Positive or negative influence on project outcome
Support or limit the project management options.
Act as inputs for the planning processes
Examples include:
  Organizational culture
  The Human Resource pool
  Marketplace conditions
  Stakeholder risk tolerance level
  Political situation
  Project Management Information Systems

## Slide 35: Expert Judgment
Advice provided by individuals having expertise in a specific knowledge area, an application area, an industry, or discipline.
Used to make informed decisions on a project.
Obtained from sources such as:
  Stakeholders
  Professionals
  Subject matter experts
  Industry groups
  The PMO
  Consultants
  Functional units

## Slide 36: Organizational Theory
Provides information on the organization of work processes and operating practices through:
  Organizational structure
  Power
  Culture
  Compensation and benefits
  Behavior of people

## Slide 37: Project Interfaces
Interface | Description
Organizational | Reporting relationships among different organizational units. They may be internal or external to the parent organization and include interfaces among the project team, upper management, other functional managers that may need to support the team, and even the organization’s customers.
Technical | Reporting relationships among technical disciplines on the project that can occur during a phase or during the transition between phases. They reflect informal and formal relationships with people on the project team and outside the team.
Interpersonal | Formal and informal reporting relationships among individuals working on the project, whether internally or externally.
Logistical | Relationships between project team members who are distributed geographically across different buildings, state, countries, and time zones.

## Slide 38: Organizational Structures
CEO
CFO
Department Head
Employee
Employee
Employee
CIO
Department Head
Employee
VP HR
Department Head
Employee
Employee

## Slide 39: Types of Organizational Structures
Organizational Structure | Description
Functional | Each department is responsible for carrying out specific activities. Reporting is hierarchical with individuals reporting to a single manager. Project manager’s authority is low, relative to the functional manager’s authority.
Matrix | Blend of functional and projectized structures. Individuals report upward in the functional hierarchy but also report horizontally to the project manager. Characterized by weak, balanced, or strong, depending on the relative authority of the project manager to the functional manager.
Projectized | Project manager and core project team operate as completely separate organizational units within the parent organization. Core project team members are completely dedicated to the project team. Team members are often co-located. Project manager reports to a program manager and has significant authority and independence.
Composite | Most modern organizations involve all of the above structures at various levels. Combination of all other types of organizational structures.

## Slide 40: Functional Organizational Structure
One departmental staff member is assigned the Project Manager role.
CEO
Staff
Staff
Staff
Staff
Staff
Staff
Production
Staff
Staff
Staff
Finance
IT

## Slide 41: Matrix Organizational Structure
Project Manager and 3 Staff assigned to project.
Resources are shared between functional areas and project.
CEO
IT
Staff
Staff
Project Manager
Staff
Staff
Staff
Production
Staff
Staff
Staff
Finance

## Slide 42: Projectized Organizational Structure
CEO
Project Manager
Staff
Staff
Staff
Staff
Staff
Staff
Project Manager
Staff
Staff
Staff
Project Manager
Each project assigned a Project Manager and 3 Staff as team members.

## Slide 43: Relative Authority in Organizational Structures
The project manager’s authority relative to the functional manager’s authority over the project and the project team.
Relationship | Functional | Matrix | Projectized
Team members are loyal to | Functional department | Conflicted loyalty | Project
Team members report to | Functional manager | Both functional manager and project manager | Project manager
Project manager’s role is | Part-time | Full-time | Full-time
Team members’ role is | Part-time | Part-time | Full-time
Control of project manager over team members is | Low | Medium | High

## Slide 44
Identifying Organizational Influences on Project Management

## Slide 45: Basics of Agile Methodology
Iterative and incremental project management approach.
Initially developed for IT software development projects but applicable for other projects.
Focuses on customer value and team empowerment.
Customer receives output and provides feedback.
Project team makes improvements based on customer feedback.
Project manager role is more facilitator than task master.
Unique processes include SCRUM, Sprint, and daily standup meetings.
The Agile Manifesto

## Slide 46: Principles of Agile
Customer Value
Iterative and Incremental Delivery
Intense Collaboration
Small and Integrated Teams
Self-Organizing Teams
Small and Continuous Improvements

## Slide 47: The Scrum Process
Planning
High-Level Design
Sprint
Sprint Review
Closure
Repeated as long as it takes to create a releasable product

## Slide 48: User Stories
Customer requirements or features.
Each user story emphasizes the functionality of the feature and how it adds to the final product.
User stories can vary in size and complexity.
Smaller stories (child) with a common theme can be combined into an epic story (parent).

## Slide 49: Scrum Roles and Responsibilities
Roles | Responsibilities
Product Owner | Consolidate and prioritize client requirements into set of deliverables. Define the features of the product based on market value. Manage project ROI and risk. Participate in all planning and review meetings. Provide answers to project team’s questions. Determine the deliverable’s review plan and communicate with stakeholders. Accept or reject work results.
Scrum Master | Resolve issues or blocks that team encounters. Enable efficient and effective team productivity and cooperation. Protect the team from external interference or disruption. Organize and facilitate Scrum-related activities and meetings. Ensure that Scrum standards are followed.

## Slide 50: Scrum Roles and Responsibilities (Cont.)
Roles | Responsibilities
Scrum Team | Select the goal and specify the work results. Organize the team and its work. Provide the product owner with work results. Work within project guidelines to reach the goal.
Stakeholders | Help product owner define the goal and vision of the project. Attend planning meetings, and occasionally attend daily team and review meetings.
Customers | Define the product requirements. Participate in review phase of each deliverable and throughout the process.

## Slide 51: Stages of the Scrum Process
Create a vision for the project
Create a Product Backlog
Set a broad release plan
Create a Sprint Backlog

## Slide 52: Product and Sprint Backlogs
A Product Backlog is a prioritized list of customer requirements and it is the first step of Scrum.
  Priority is based on the riskiness and business value of the user story.
  The Product Owner creates the Product Backlog based on a Sprint Backlog user story and input from stakeholders.
  A Product Backlog can hold items of varying size.
A Sprint Backlog is a list of user stories selected from the Product Backlog chosen by the Scrum Team.
  The Scrum Team decides on the work that creates a deliverable at the end.
  After team decides on the Sprint Backlog, nothing more can be added to the list during the cycle.
  Any new customer requirements or additional stories are added to the Product Backlog, not to the Sprint Backlog.

## Slide 53: The Sprint Cycle
Sprint Deliverable
Sprint Review
Sprint Review
Sprint
Backlog
Sprint
Sprint Planning Meeting
Sprint Closure
1-4 Week Sprint
Tasks for the Sprint
Tasks from the Product Backlog
Hand off deliverables
Demo of the deliverables
Fixed deadline and deliverables

## Slide 54: Iterative Approach
Customer provides early feedback to the team.
Feedback helps develop subsequent Sprints.
A Sprint is completed on a set date whether or not the work is completed.
If a team is unable to meet the set target at the end of a Sprint, then the team is expected to acknowledge that it did not achieve set goals.
Incomplete tasks are then added to the product backlog.
No downtime between Sprints.
One Sprint Review leads to the next Sprint planning meeting

## Slide 55: Burndown Charts
Tracks the progress of the project.
Plots the number of days of Sprint against the number of hours of work remaining.
Supporting Data:

## Slide 56: Daily Standup Meetings
Short, 15-minute meetings.
Conducted with team members standing in a circle—resembling a huddle.
Ideally at the beginning of the work day.
Enables teams to organize themselves.
Team members summarize:
  The tasks that were completed the previous day.
  Tasks to be completed today.
  Any roadblocks that team is facing.
Discuss solutions for complicated problems offline.

## Slide 57: The Closure Process
Sprint retrospective
Starting next Sprint
Release planning

## Slide 58: Agile Comparison to Other Methodologies
Agile
Informal
Iterative
Not linear
Incremental deliverables
Focus on people and collaboration
Respond to lessons learned
Others
Formal
Sequential
Linear
Single final deliverable or product
Focus on process and tools
Follow the plan
Other project management methodologies include PMBOK, PRINCE2, and Waterfall.

## Slide 59
Describing Agile Methodology

## Slide 60
What types of project management experiences have you had?
How does the ability to tailor each of the project management process groups to each project or phase improve your chances of project success?